## Sheet1
FreshGuard - Guarding Food From Waste
Work Breakdown Structure
WBS ID | Activity / Task | Milestone/ Deliverable | Effort (hrs) | Duration (days) | Precedence | Resources | Start Date | End Date | Simran Gopali | Sujata Bajracharya | Shraddha Sedhai
1.1 | Determine Project Title |  | 1 | 0.5 | NIL | All Team | Week 1 Mon | Week 1 Mon | 33% | 33% | 33%
1.2 | Write the Overview |  | 2 | 1 | 1.1 | All Team | Week 1 Tue | Week 1 Tue | 33% | 33% | 33%
1.3 | Write Project Aims |  | 2 | 1 | 1.2 | All Team | Week 1 Wed | Week 1 Wed | 33% | 33% | 33%
1.4 | Write Project Objectives |  | 2 | 1 | 1.3 | All Team | Week 1 Thu | Week 1 Thu | 33% | 33% | 33%
1.5 | Write Project Scope |  | 2 | 1 | 1.4 | All Team | Week 1 Fri | Week 1 Fri | 33% | 33% | 33%
1.6.1 | Derive Work Breakdown Structure |  | 3 | 1 | 1.5 | Simran Gopali | Week 2 Mon | Week 2 Mon | 100%
1.6.2 | Determine Milestones / Deliverables |  | 2 | 1 | 1.6.1 | Sujata Bajracharya | Week 2 Tue | Week 2 Tue |  | 100%
1.6.3 | Derive Gantt Chart |  | 4 | 2 | 1.6.2 | Simran Gopali | Week 2 Wed | Week 2 Thu | 100%
1.7 | Gantt Chart File (.gan) | Milestone | 1 | 1 | 1.6.3 | Simran Gopali | Week 2 Fri | Week 2 Fri | 100%
1.8.1 | Development Platform & Tools |  | 2 | 1 | 1.6.3 | Sujata Bajracharya | Week 2 Wed | Week 2 Wed |  | 100%
1.8.2 | Demonstration Platform |  | 1 | 1 | 1.8.1 | Shraddha Sedhai | Week 2 Thu | Week 2 Thu |  |  | 100%
1.9 | Risk Management Plan |  | 3 | 1 | 1.8.2 | Shraddha Sedhai | Week 2 Fri | Week 2 Fri |  |  | 100%
1.1 | Review Format & Proofread (Task 1) |  | 2 | 1 | 1.9 | All Team | Week 3 Mon | Week 3 Mon | 33% | 33% | 33%
1.11 | Turnitin Check & HLMS Submission - Task 1 | Milestone | 1 | 1 | 1.1 | Simran Gopali | Week 3 Tue | Week 3 Tue | 100%
2.1 | Determine Functional Requirements |  | 2 | 1 | 1.11 | Group | Week 3 Wed | Week 3 Wed
2.2 | Determine Non-Functional Requirements |  | 2 | 1 | 2.1 | Group | Week 3 Thu | Week 3 Thu
2.3.1 | UC1 - Register User & Privacy Settings |  | 6 | 3 | 2.2 | Simran Gopali | Week 3 Fri | Week 5 Tue | 100%
2.3.2 | UC4 - Food Analytics |  | 6 | 3 | 2.2 | Simran Gopali | Week 3 Fri | Week 5 Tue | 100%
2.3.3 | UC2- Manage Food Inventory |  | 6 | 3 | 2.2 | Sujata Bajracharya | Week 3 Fri | Week 5 Tue |  | 100%
2.3.4 | UC5 - View Notifications |  | 6 | 3 | 2.3.3 | Sujata Bajracharya | Week 3 Fri | Week 5 Tue |  | 100%
2.3.5 | UC3 - Browse Food Items |  | 6 | 3 | 2.2 | Shraddha Sedhai | Week 3 Fri | Week 5 Tue |  |  | 100%
2.3.6 | UC6 - Plan Weekly Meals |  | 6 | 3 | 2.3.5 | Shraddha Sedhai | Week 3 Fri | Week 5 Tue |  |  | 100%
2.4 | Requirements Specification Document | Milestone | 2 | 1 | 2.3.6 | Group | Week 5 Wed | Week 5 Wed
3.1 | Architectural Design (Deployment Diagram) |  | 4 | 2 | 2.4 | Group | Week 5 Thu | Week 5 Fri
3.2 | Site Map (Hierarchy Diagram) |  | 2 | 1 | 3.1 | Group | Week 6 Mon | Week 6 Mon
3.3.1 | Wireframes - UC1 Register & UC4 Analytics |  | 4 | 2 | 2.4 | Simran Gopali | Week 5 Thu | Week 5 Fri | 100%
3.3.2 | Wireframes - UC2 Inventory & UC5 Notifications |  | 4 | 2 | 3.3.1 | Sujata Bajracharya | Week 6 Mon | Week 6 Tue |  | 100%
3.3.3 | Wireframes - UC3 Browse & UC6 Meal Plans |  | 4 | 2 | 3.3.2 | Shraddha Sedhai | Week 6 Wed | Week 6 Thu |  |  | 100%
3.4.1 | ERD (Conceptual View) |  | 4 | 2 | 3.2 | Sujata Bajracharya | Week 6 Tue | Week 6 Wed |  | 100%
3.4.2 | Data Dictionary |  | 4 | 2 | 3.4.1 | Group | Week 6 Thu | Week 6 Fri
3.5 | Review Format & Proofread (Design) |  | 2 | 1 | 3.4.2 | All Team | Week 7 Mon | Week 7 Mon | 33% | 33% | 33%
3.6 | Design Document Complete | Milestone | 1 | 1 | 3.5 | Group | Week 7 Tue | Week 7 Tue
4.1 | Project Setup (React/Firebase/Git) |  | 4 | 2 | 3.6 | Group | Week 7 Wed | Week 7 Thu
4.2 | Implement UC1 - Register User & Privacy Settings |  | 8 | 4 | 4.1 | Simran Gopali | Week 7 Fri | Week 8 Wed | 100%
4.3 | Implement UC4- Food Analytics |  | 10 | 5 | 4.1 | Simran Gopali | Week 7 Fri | Week 8 Thu | 100%
4.4 | Implement UC3 - Browse Food Items |  | 8 | 4 | 4.1 | Shraddha Sedhai | Week 7 Fri | Week 8 Wed |  |  | 100%
4.5 | Unit Testing - Iteration 1 |  | 4 | 2 | 4.2,4.3,4.4 | All Team | Week 8 Fri | Week 9 Mon | 33% | 33% | 33%
4.6 | Integration Testing - Iteration 1 |  | 4 | 2 | 4.5 | Group | Week 9 Tue | Week 9 Wed
4.7 | Iteration 1 Prototype Complete | Milestone | 1 | 1 | 4.6 | Group | Week 9 Thu | Week 9 Thu
5.1 | Implement UC2-Manage Food Inventory |  | 8 | 4 | 4.7 | Sujata Bajracharya | Week 9 Fri | Week 10 Wed |  | 100%
5.2 | Implement UC5 - View Notifications |  | 8 | 4 | 4.7 | Sujata Bajracharya | Week 9 Fri | Week 10 Wed |  | 100%
5.3 | Implement UC6 - Plan Weekly Meals |  | 10 | 5 | 4.7 | Shraddha Sedhai | Week 9 Fri | Week 10 Thu |  |  | 100%
5.4 | Unit Testing - Iteration 2 |  | 4 | 2 | 5.1,5.2,5.3 | All Team | Week 10 Fri | Week 11 Mon | 33% | 33% | 33%
5.5 | System Integration Testing |  | 4 | 2 | 5.4 | Group | Week 11 Tue | Week 11 Wed
5.6 | Iteration 2 Complete - Full System | Milestone | 1 | 1 | 5.5 | Group | Week 11 Thu | Week 11 Thu
6.1 | End-to-End System Testing |  | 6 | 3 | 5.6 | Group | Week 11 Fri | Week 12 Tue
6.2 | User Acceptance Testing (UAT) |  | 4 | 2 | 6.1 | All Team | Week 12 Wed | Week 12 Thu | 33% | 33% | 33%
6.3 | Bug Fixing & Optimization |  | 6 | 3 | 6.2 | All Team | Week 12 Fri | Week 13 Tue | 33% | 33% | 33%
6.4 | Documentation Finalization |  | 4 | 2 | 6.3 | All Team | Week 13 Wed | Week 13 Thu | 33% | 33% | 33%
6.5 | Final Review & Proofread |  | 2 | 1 | 6.4 | All Team | Week 13 Fri | Week 13 Fri | 33% | 33% | 33%
6.6 | Turnitin Check & HLMS Submission - Task 2 | Milestone | 1 | 1 | 6.5 | Simran Gopali | Week 14 Mon | Week 14 Mon | 100%
S.N: | Person Responsible | Color Legend
1 | Simran Gopali | green
2 | Sujata Bajracharya | orange
3 | Shraddha Sedhai | purple
4 | Group Work - shared responsibility | yellow