## SavePlate WBS
SavePlate – Smart Food Waste Reduction App
BIT216 Software Engineering Principles ¦ Assignment 1 |  |  |  |  | Student A | Student B | Student C | Group
WBS ID | Activity / Task | Milestone / Deliverable | Duration (days) | Precedence | Simran Gopali (UC1, UC2) | Sujata Bajracharya (UC3, UC4) | Shraddha Sedhai (UC5, UC6) | Group
1 | PLANNING |  |  | NIL |  |  |  | 100
1.1 | Determine Project Title |  | 0.5 | NIL | 33 | 33 | 33
1.2 | Write the Overview |  | 1 | 1.1 | 33 | 33 | 33
1.3 | Write the Project Aims |  | 1 | 1.2 | 33 | 33 | 33
1.4 | Write the Project Objectives |  | 1 | 1.3 | 33 | 33 | 33
1.5 | Write the Project Scope |  | 1 | 1.4 | 33 | 33 | 33
1.6 | Project Schedule |  |  | 1.5
1.6.1 | Derive WBS |  | 1 | 1.5 |  |  |  | 100
1.6.2 | Determine Milestones / Deliverables |  | 1 | 1.6.1 |  |  |  | 100
1.6.3 | Derive Gantt Chart (.gan) |  | 2 | 1.6.2 |  |  |  | 100
1.7 | Gantt Chart File (.gan) | Milestone/Deliverable | 1 | 1.6.3 |  |  |  | 100
1.8 | Technical Description of Proposed System |  | 2 | 1.6.3 |  |  |  | 100
1.8.1 | Development Platform & Tools |  | 1 | 1.6.3 |  |  |  | 100
1.8.2 | Demonstration Platform |  | 1 | 1.8.1 |  |  |  | 100
1.9 | Risk Management Plan |  | 1 | 1.8 |  |  |  | 100
1.10 | Review, Format & Proofread Document |  | 1 | 1.9 |  |  |  | 100
1.11 | Turnitin Check & HLMS Submission – Task 1 | Milestone/Deliverable | 1 | 1.10 |  |  |  | 100
2 | REQUIREMENTS |  |  | 1.11
2.1 | Determine Functional Requirements |  | 1 | 1.11 |  |  |  | 100
2.2 | Determine Non-Functional Requirements |  | 1 | 2.1 |  |  |  | 100
2.3 | Modelling Requirements (Epics, User Stories, AC, Tasks) |  |  | 2.2
2.3.1 | UC1 - Register User and Privacy Settings (Epic + Stories + AC + Tasks) |  | 3 | 2.2 | 100
2.3.2 | UC2 - Manage Food Inventory (Epic + Stories + AC + Tasks) |  | 3 | 2.3.1 | 100
2.3.3 | UC3 - Browse Food Items (Epic + Stories + AC + Tasks) |  | 3 | 2.2 |  | 100
2.3.4 | UC4 - Food Analytics (Epic + Stories + AC + Tasks) |  | 3 | 2.3.3 |  | 100
2.3.5 | UC5 - View Notification (Epic + Stories + AC + Tasks) |  | 3 | 2.2 |  |  | 100
2.3.6 | UC6 - Plan Weekly Meals (Epic + Stories + AC + Tasks) |  | 3 | 2.3.5 |  |  | 100
2.4 | Requirements Specification Document (.docx) | Milestone/Deliverable | 1 | 2.3.6 |  |  |  | 100
3 | DESIGN |  |  | 2.4
3.1 | Architectural Design (Deployment Diagram) |  | 2 | 2.4 |  |  |  | 100
3.2 | Site Map (Hierarchy Diagram) |  | 1 | 3.1 |  |  |  | 100
3.3 | UX / Wireframes |  |  | 2.4
3.3.1 | Wireframes – UC1 Register User & UC4 Food Analytics |  | 2 | 2.4 | 100
3.3.2 | Wireframes – UC2 Manage Inventory & UC5 Notifications |  | 2 | 3.3.1 |  | 100
3.3.3 | Wireframes – UC3 Browse Food Items & UC6 Weekly Meals |  | 2 | 3.3.2 |  |  | 100
3.4 | Database Design |  |  | 3.2
3.4.1 | ERD (Conceptual View) |  | 2 | 3.2 |  |  |  | 100
3.4.2 | Data Dictionary |  | 2 | 3.4.1 |  |  |  | 100
3.5 | Review, Format & Proofread Document |  | 1 | 3.4.2 |  |  |  | 100
3.6 | Turnitin Check & HLMS Submission – Task 2 | Milestone/Deliverable | 1 | 3.5 |  |  |  | 100
UC
Simran Gopali |  | UC1- Register user and privacy setting, UC2- Manage Food and Inventory
Sujata Bajracharya |  | UC3- Browse Food Items, UC4- Food Analytics
Shraddha Sedhai |  | UC5- View Notification, UC6- Plan Weekly Meals
Group |  | All team members collaborate on this task
Milestone/Deliverable |  | Formal submission or key project checkpoint