## 1.0 Project Overview

FreshGuard is a smart mobile/web app that aims to contribute in a meaningful way towards the reduction of food waste in Malaysian homes. The platform features smart food management, expiry reminders, donating food and responsible meal planning along with excellent user data protection and account security.

Recent studies show that the amount of food waste produced at the household level is significant among Malaysians. FreshGuard directly tackles this issue by offering a centralized system to manage and keep track of what they have, plan their meals, distribute excess food to the community and get reminders when food runs out.

## 2.0 Project Aims

FreshGuard aims to:

- Minimize food waste in the home by using a smart inventory system and expiry reminders.

- Allow users to choose from menu items according to the ingredients available.

- Enable surplus food donations in the community.

- Offer useful insights and analytics to encourage users to continue their greener lifestyle.

- Provide user privacy and data security with user settings and two factor authentication.

## 3.0 Project Objectives

At the project's completion, FreshGuard will:

- Work on the secure user registration and user authentication component with 2FA and privacy settings support (UC1).

- To have a food inventory system in place that tracks expiry and converts food into donations (UC2).

- Implement a community food browsing module, where individuals can view and take the food that is donated (UC3).

- Develop an analytics dashboard to present food saving impact in charts and with progress indicators (UC4).

- Implement an intelligent notification system for reminder notifications, donation updates, and meal reminder notifications (UC5).

- Create a weekly meal plan that connects ingredients and recipes, and sets reminders (UC6).

## 4.0 Project Scope

### In Scope:

- Users' registration, login, and privacy/security settings management (2FA support).

- Manage food inventory: Add, edit, delete, mark as used, convert to donation.

- Browsing for donations by the community: filtering, viewing details, requesting/claiming items.

- Food analytics dashboard: visual reports of number of foods saved and donated.

- Push notification and in-app reminders for meal, donation and expiration dates.

- Weekly menus and detailed inventory with suggested recipes.

### Out of Scope:

- Payments for food orders online or integrated into the learning platform.

- Integration of third-party grocery store API.

- Logistics or physical food transport services.

- Integration with Government food waste databases.

## 5.0 Development Platform & Tools

| Description | Selected Technology / Tool |
| --- | --- |
| Frontend Framework | React.js (Web) / React Native (Mobile). |
| Backend & Database | Firebase (Firestore, Authentication, Cloud Functions) |
| Version Control | Git with GitHub (feature-branch workflow) |
| Project Management | GitHub Projects (Kanban board), GanttProject (.gan) |
| UI Design & Wireframes | Figma |
| IDE | Visual Studio Code |
| Testing | Jest (unit), Cypress (E2E), Firebase Emulator Suite |
| Demonstration Platform | Vercel (web deployment) / Expo Go (mobile preview). |

## 6.0 Risk Management Plan

| Risk | Likelihood | Impact | Priority | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| Illness or academic conflict with team member | Medium | High | High | Maintain up-to-date documentation; redistribute task early; weekly check-ins. |
| Scope creep – feature additions outside the scope | High | Medium | High | Review scope baseline; ask team leader's permission for scope changes. |
| Firebase quota limits in development and testing | Low | Medium | Medium | Monitor usage; test locally with Firebase Emulator Suite. |
| Integration testing between the front-end and the Firebase back-end | Medium | High | High | After every iteration, conduct integration testing of the front-end components with the back-end Firebase. |
| Data privacy non-compliance (PDPA Malaysia) | Low | High | High | Adhere to PDPA guidelines and ensure 2FA, data minimisation, consent mechanisms are in place. |
| Miscommunication between team members | Medium | Medium | Medium | Weekly team meetings, shared Notion/Github board, clear task Ownership. |

7.0 Work Breakdown Structure – Sujata Bajracharya

The following WBS rows highlight tasks assigned to Me (Sujata Bajracharya) in addition to all shared team tasks.

| WBS ID | Task / Activity | Effort (hrs) | Duration (days) | Precedence | Resources |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Determine Project Title | 1 | 0.5 | NIL | All Team |
| 1.2 | Write the Overview | 2 | 1 | 1.1 | All Team |
| 1.3 | Write Project Aims | 2 | 1 | 1.2 | All Team |
| 1.4 | Write Project Objectives | 2 | 1 | 1.3 | All Team |
| 1.5 | Write Project Scope | 2 | 1 | 1.4 | All Team |
| 1.6.1 | Derive Work Breakdown Structure | 3 | 1 | 1.5 | Group |
| 1.6.2 | Determine Milestones / Deliverables | 2 | 1 | 1.6.1 | Group |
| 1.6.3 | Derive Gantt Chart | 4 | 2 | 1.6.2 | Group |
| 1.7 | Gantt Chart File (.gan) — MILESTONE | 1 | 1 | 1.6.3 |  |
| 1.8.1 | Development Platform & Tools | 2 | 1 | 1.6.3 | Group |
| 1.8.2 | Demonstration Platform | 1 | 1 | 1.8.1 | Group |
| 1.9 | Risk Management Plan | 3 | 1 | 1.8 | Group |
| 1.10 | Review Format & Proofread (Task 1) | 2 | 1 | 1.9 | All Team |
| 1.11 | Turnitin Check & HLMS Submission Task 1 — MILESTONE | 1 | 1 | 1.10 | All Team |
| 2.1 | Determine Functional Requirements | 2 | 1 | 1.11 | Group |
| 2.2 | Determine Non-Functional Requirements | 2 | 1 | 2.1 | Group |
| 2.3 | Create Software Design Specifications | 2 | 1 | 2.2 | Group |
| 2.3.3 | UC3 - Browse Food Items | 6 | 3 | 2.2 | Sujata Bajracharya |
| 2.3.4 | UC4 - Food Analytics | 6 | 3 | 2.3.3 |  |
| 2.4 | Requirements Specification Document — MILESTONE | 2 | 1 | 2.3.6 | Group |
| 3.1 | Architectual Design (Deployment Diagram) | 4 | 2 | 2.4 | Group |
| 3.2 | Architectural Design (Portfolio) | 4 | 3 | 2.3 | Group |
| 3.3.2 | Wireframes – UC2 (Inventory) & UC5 (Notifications) | 4 | 2 | 3.3.1 | Sujata Bajracharya |
| 3.4.1 | ERD (Conceptual View) | 4 | 2 | 3.2 | Group |
| 3.4.2 | Data Dictionary | 4 | 2 | 3.4.1 | Group |
| 3.5 | Review Format & Proofread (Design) | 2 | 1 | 3.4.2 | All Team |
| 3.6 | Design Document Complete - MILESTONE | 1 | 1 | 3.5 | Group |
| 4.1 | Project Setup (React/Firebase/Git) | 4 | 2 | 3.6 | Group |
| 4.4 | Implement UC3 - Browse Food Items | 8 | 4 | 4.1 | Sujata Bajracharya |
| 4.5 | Unit Testing – Iteration 1 | 4 | 2 | 4.2,4.3,4.4 | All Team |
| 4.6 | Integration Testing – Iteration 1 | 4 | 2 | 4.5 | Group |
| 4.7 | Iteration 1 Prototype Complete - MILESTONE | 1 | 1 | 4.6 | Group |
| 5.1 | Implement UC4 - Food Analytics | 8 | 4 | 4.7 | Sujata Bajracharya |
| 5.4 | Unit Testing - Iteration 2 | 4 | 2 | 5.1,5.2,5.3 | All Team |
| 5.5 | System Integration Testing | 4 | 2 | 5.4 | Group |
| 5.6 | Iteration 2 Complete — MILESTONE | 1 | 1 | 5.5 | Group |
| 6.1 | End-to-End System Testing | 6 | 3 | 5.6 | Group |
| 6.2 | User Acceptance Testing (UAT) | 4 | 2 | 6.1 | All Team |
| 6.3 | Bug Fixing & Optimization | 6 | 3 | 6.2 | All Team |
| 6.4 | Documentation Finalization | 2 | 1 | 6.4 | All Team |
| 6.5 | Final Review & Proofread | 2 | 1 | 6.4 | All Team |
| 6.6 | Turnitin Check & HLMS Submission Task 2 — MILESTONE | 1 | 1 | 6.5 | All Team |

## 8.0 Project Schedule

The project will take 14 weeks to complete and will be broken down into four major stages: Proposal (Weeks 1-3), Requirements & Design (Weeks 3-7), Implementation (Weeks 7-11), and Testing & ubmission (Weeks 11-14). The entire Gantt Chart is available in a separate GanttProject file (FreshGuard _Gantt.gan).

| Phase | Week Range |
| --- | --- |
| Phase 1 – Project Proposal | Weeks 1 – 3 |
| Phase 2 – Requirements Specification | Weeks 3 - 5 |
| Phase 3 – Design & Architecture | Weeks 5 – 7 |
| Phase 4 – Implementation Iteration 1 | Weeks 7 – 9 |
| Phase 5 – Implementation Iteration 2 | Weeks 9 – 11 |
| Phase 6 – Testing & Final Submission | Weeks 11 – 14 |

## 9.0 Use Cases – Sujata Bajracharya

## Use Case 3: Search for food products

| Use Case ID | UC3 |
| --- | --- |
| Use Case Name | Browse Food Items |
| Goal in Context | Allows potential household food recipients to see available foods from the inventory and/or the donation list from other households, so that they can make a claim for the food or plan their meals. |
| Primary Actor | Household User |
| Pre-Condition | User must be logged into the system. |
| Trigger | User selects to view the available food items in inventory or donations |
| Typical Course of Events | 1. User clicks on 'Browse Food Items'. 2. System provides filtering capabilities: Inventory Only, Donation Listings, Categories, Expiry Date, Storage Type. 3. User clicks on filters or view all. 4. All the item details - Name, Quantity, Expiry Date, Pickup Location, and Contact Method are displayed in the system. 5. User clicks on one of the items to obtain more information. 6. System displays all the item information (category, storage location, notes). 7. User can indicate if it is a Used Item, a Meal Plan, or is Flagged for Donation. 8. System updates item status as necessary. |
| Alternative Course of Events | Line 3a: If no items found with selected filters, system displays: 'No items found. Please do not change your filters. Line 7a: If an item is marked for donation, a system prompt will appear for where the item should be picked up and when, to generate a Donation List. |

### Use Case 4 : Food Analytics

| Use Case ID | UC4 |
| --- | --- |
| Use Case Name | Food Analytics |
| Goal in Context | Describes how the system tracks food-saving activities and generates visual reports to reflect user impact, promoting continuous engagement. |
| Primary Actor | Household User |
| Pre-Condition | User should have an item in the food system, marked as used, or donated. |
| Trigger | User clicks on ‘Track My Impact' or ‘Reports' on the dashboard |
| Typical Course of Events | 1. User clicks 'Track and Report' on the dashboard. 2. System pulls the logged activities (used items/donated items) from inventory and donation records. 3. User views the summary dashboard. 4. System shows charts and progress indicators for: Total food saved from waste, Number of donations made. 5. Users click on certain data or certain time ranges. 6. System updates the report view depending on the filters applied, monthly, weekly, by category. |
| Alternative Course of Events | Line 3a: If no food saving data is located, the system will display a message to the user to start logging and donating food to be able to see progress. |