## SavePlate WBS
SavePlate – Smart Food Waste Reduction App
[12 empty] | Member 1 (UC1,UC2) | Member 2 (UC3,UC4) | Member 3 (UC5,UC6)
# | Task No | Task Name (L1) |  | Task Name (L2) |  | Task Name (L3) |  | Task Name (L4) | Milestone / Deliverable | Duration (days) | Precedence | Member 1 (UC1,UC2) | Member 2 (UC3,UC4) | Member 3 (UC5,UC6)
1 | 1 | Planning
2 |  |  | 1.1 | Determine Project Title | [5 empty] | 1 | NIL | 100% | 100% | 100%
3 |  |  | 1.2 | Write Overview (motivation, users, cost, timeline) | [5 empty] | 1 | NIL | 100%
4 |  |  | 1.3 | Write Project Aims | [5 empty] | 1 | 1.2 |  | 100%
5 |  |  | 1.4 | Write Project Objectives (SMART) | [5 empty] | 1 | 1.3 |  |  | 100%
6 |  |  | 1.5 | Define Project Scope | [5 empty] | 1 | 1.4 | 100% | 100% | 100%
7 |  |  |  |  | 1.5.1 | Define in-scope features (6 use cases) |  |  |  | 1 | 1.4 | 100%
8 |  |  |  |  | 1.5.2 | Define out-of-scope features |  |  |  | 1 | 1.5.1 |  | 100%
9 |  |  | 1.6 | Project Schedule | [6 empty] | 1.5
10 |  |  |  |  | 1.6.1 | Derive Work Breakdown Structure (WBS) |  |  |  | 1 | 1.5 | 100% | 100% | 100%
11 |  |  |  |  | 1.6.2 | Determine Milestones & Deliverables |  |  |  | 1 | 1.6.1 | 100% | 100% | 100%
12 |  |  |  |  | 1.6.3 | Derive Gantt Chart (GanttProject .gan file) |  |  |  | 1 | 1.6.2 | 100% | 100% | 100%
13 |  |  | 1.7 | Define Technical Platform | [5 empty] | 1 | 1.5 |  |  | 100%
14 |  |  |  |  | 1.7.1 | Documentation tools (MS Word / Google Docs) |  |  |  | 1 | 1.5 |  |  | 100%
15 |  |  |  |  | 1.7.2 | Modelling tools (draw.io / Lucidchart) |  |  |  | 1 | 1.7.1 |  |  | 100%
16 |  |  |  |  | 1.7.3 | Design tools (Figma / Canva) |  |  |  | 1 | 1.7.2 |  |  | 100%
17 |  |  |  |  | 1.7.4 | Project management – GanttProject |  |  |  | 1 | 1.7.3 |  |  | 100%
18 |  |  |  |  | 1.7.5 | Version control – GitHub |  |  |  | 1 | 1.7.4 |  |  | 100%
19 |  |  |  |  | 1.7.6 | Frontend & Backend framework |  |  |  | 1 | 1.7.5 |  |  | 100%
20 |  |  |  |  | 1.7.7 | Hardware & Demo environment specs |  |  |  | 1 | 1.7.6 |  |  | 100%
21 |  |  | 1.8 | Derive Risk Management Plan | [5 empty] | 1 | 1.7 | 100% | 100% | 100%
22 |  |  |  |  | 1.8.1 | Identify project risks (min 5) |  |  |  | 1 | 1.7 | 100% | 100% | 100%
23 |  |  |  |  | 1.8.2 | Assign probability & impact (L/M/H) |  |  |  | 1 | 1.8.1 | 100% | 100% | 100%
24 |  |  |  |  | 1.8.3 | Define mitigation strategies |  |  |  | 1 | 1.8.2 | 100% | 100% | 100%
⭐ MILESTONE / DELIVERABLE: Project Proposal / Plan
26 | 2 | Requirements
27 |  |  | 2.1 | Requirements Definition | [6 empty] | NIL
28 |  |  |  |  | 2.1.1 | List Functional Requirements |  |  |  | 2 | NIL | 100% | 100% | 100%
29 |  |  |  |  | 2.1.2 | List Non-Functional Requirements |  |  |  | 2 | 2.1.1 | 100% | 100% | 100%
30 | [6 empty] | 2.1.2.1 | Security – 2FA, password encryption, data privacy |  | 1 | 2.1.1 | 100%
31 | [6 empty] | 2.1.2.2 | Performance – page loads within 3 seconds |  | 1 | 2.1.2.1 |  | 100%
32 | [6 empty] | 2.1.2.3 | Usability – accessible on mobile & desktop |  | 1 | 2.1.2.2 |  |  | 100%
33 | [6 empty] | 2.1.2.4 | Reliability – 99% system uptime |  | 1 | 2.1.2.3 | 100%
34 |  |  | 2.2 | Requirements Modelling (User Stories) | [6 empty] | 2.1
35 |  |  |  |  | 2.2.1 | UC1 – Register User & Privacy Settings [Member 1] |  |  |  |  | 2.1 | 100%
36 | [6 empty] | 2.2.1.1 | Write Epic |  | 1 | 2.1 | 100%
37 | [6 empty] | 2.2.1.2 | Write User Stories + Acceptance Criteria |  | 2 | 2.2.1.1 | 100%
38 | [6 empty] | 2.2.1.3 | Assign MoSCoW priority (Must/Should/Could/Won't) |  | 1 | 2.2.1.2 | 100%
39 | [6 empty] | 2.2.1.4 | Define development Tasks |  | 1 | 2.2.1.3 | 100%
40 |  |  |  |  | 2.2.2 | UC2 – Manage Food Inventory [Member 1] |  |  |  |  | 2.1 | 100%
41 | [6 empty] | 2.2.2.1 | Write Epic |  | 1 | 2.1 | 100%
42 | [6 empty] | 2.2.2.2 | Write User Stories + Acceptance Criteria |  | 2 | 2.2.2.1 | 100%
43 | [6 empty] | 2.2.2.3 | Assign MoSCoW priority |  | 1 | 2.2.2.2 | 100%
44 | [6 empty] | 2.2.2.4 | Define development Tasks |  | 1 | 2.2.2.3 | 100%
45 |  |  |  |  | 2.2.3 | UC3 – Browse Food Items [Member 2] |  |  |  |  | 2.1 |  | 100%
46 | [6 empty] | 2.2.3.1 | Write Epic |  | 1 | 2.1 |  | 100%
47 | [6 empty] | 2.2.3.2 | Write User Stories + Acceptance Criteria |  | 2 | 2.2.3.1 |  | 100%
48 | [6 empty] | 2.2.3.3 | Assign MoSCoW priority |  | 1 | 2.2.3.2 |  | 100%
49 | [6 empty] | 2.2.3.4 | Define development Tasks |  | 1 | 2.2.3.3 |  | 100%
50 |  |  |  |  | 2.2.4 | UC4 – Food Analytics [Member 2] |  |  |  |  | 2.1 |  | 100%
51 | [6 empty] | 2.2.4.1 | Write Epic |  | 1 | 2.1 |  | 100%
52 | [6 empty] | 2.2.4.2 | Write User Stories + Acceptance Criteria |  | 2 | 2.2.4.1 |  | 100%
53 | [6 empty] | 2.2.4.3 | Assign MoSCoW priority |  | 1 | 2.2.4.2 |  | 100%
54 | [6 empty] | 2.2.4.4 | Define development Tasks |  | 1 | 2.2.4.3 |  | 100%
55 |  |  |  |  | 2.2.5 | UC5 – View Notifications [Member 3] |  |  |  |  | 2.1 |  |  | 100%
56 | [6 empty] | 2.2.5.1 | Write Epic |  | 1 | 2.1 |  |  | 100%
57 | [6 empty] | 2.2.5.2 | Write User Stories + Acceptance Criteria |  | 2 | 2.2.5.1 |  |  | 100%
58 | [6 empty] | 2.2.5.3 | Assign MoSCoW priority |  | 1 | 2.2.5.2 |  |  | 100%
59 | [6 empty] | 2.2.5.4 | Define development Tasks |  | 1 | 2.2.5.3 |  |  | 100%
60 |  |  |  |  | 2.2.6 | UC6 – Plan Weekly Meals [Member 3] |  |  |  |  | 2.1 |  |  | 100%
61 | [6 empty] | 2.2.6.1 | Write Epic |  | 1 | 2.1 |  |  | 100%
62 | [6 empty] | 2.2.6.2 | Write User Stories + Acceptance Criteria |  | 2 | 2.2.6.1 |  |  | 100%
63 | [6 empty] | 2.2.6.3 | Assign MoSCoW priority |  | 1 | 2.2.6.2 |  |  | 100%
64 | [6 empty] | 2.2.6.4 | Define development Tasks |  | 1 | 2.2.6.3 |  |  | 100%