Table of Contents

1.0 Project Overview	2

2.0 Project Aims	2

3.0 Project Objectives	3

4.0 Project Scope	4

5.0 Development Platform & Tools	5

6.0 Risk Management Plan	6

7.0 Work Breakdown Structure – Shraddha Sedhai	7

8.0 Project Schedule	12

9.0 Use Cases	13

Use Case 5: View Notifications	13

Use Case 6: Food Analytics	14

# 1.0 Project Overview

FreshGuard is an intelligent mobile/web tool that can help Malaysian households to greatly minimize food waste. It's a platform that integrates intelligent food inventory, expiry notification, donation support and responsible meal planning with robust user data privacy and account security.

Recent research showed that there is significant amount of food waste produced by the Malaysian households. FreshGuard directly addresses this challenge by giving the users a single platform to keep track of what they have, do planning, share excess food with the community and timely reminders about food expiring.

# 2.0 Project Aims

FreshGuard aims to:

- Minimize household food waste by intelligent inventory management and expiry alerts.

- Allowing deference to users' choice in meal planning when ingredients are limited.

- Increase the supply of surplus food in local communities.

- Offer meaningful analytics to encourage users to maintain eco-friendly practices.

- Provide users with user privacy and data security: Configurable account settings, two factor authentication.

# 3.0 Project Objectives

At the conclusion of the project, FreshGuard will:

- Implement a secure user registration and authentication mechanism with 2FA and privacy settings (UC1).

- Adopt a detailed food inventory system that has expiry tracking and food donation conversion system (UC2).

- Create a community food BROWSE module that will enable viewing and claiming of available donations (UC3).

- Develop an analytics dashboard to visually show food-saving impact in charts and progress indicators (UC4).

- UC5: Implement a smart notification system for reminder messages about food and meal expiration, donation updates, etc.

- Provide a weekly meal plan that ties inventory items to recipes and provides reminders (UC6).

# 4.0 Project Scope

In Scope:

- User sign up, login and privacy/security settings (2FA support).

- Add, Edit, Delete, Mark as used, Convert to donation for Food inventory management.

- Community donation browsing: filter, view details, request items / claim items.

- Food analytics dashboard: visual reports of food saved and food donated.

- Send reminders, notifications and alerts about meals, donation activity and expiry dates.

- Weekly meal planning with current inventory and suggestions for recipes.

Out of Scope:

- Online ordering or payment options for food.

- Third party grocery store API integration.

- Delivery logistics, or physical transportation of food.

- Linking to Government food waste databases.

# 5.0 Development Platform & Tools

| Description | Selected Tool |
| --- | --- |
| Frontend Framework | React.js (Web) / React Native (Mobile). |
| Backend & Database | Firebase (Firestore, Authentication, Cloud Functions) |
| Version Control | Git with GitHub (feature-branch workflow) |
| Project Management | GitHub Projects, GanttChart |
| UI Design & Wireframes | Figma |
| IDE | Visual Studio Code |
| Testing | Jest (unit), Cypress (E2E), Firebase Emulator Suite |
| Demonstration Platform | Vercel (web deployment) / Expo Go (mobile preview). |

# 6.0 Risk Management Plan

| Risk | Likelihood | Impact | Priority | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| Team member unavailability due to illness or academic conflicts | Medium | High | High | Maintain up-to-date documentation; redistribute task early; weekly check-ins. |
| Scope creep – feature additions outside the scope | High | Medium | High | Review scope baseline; ask team leader's permission for scope changes. |
| Firebase quota limits in development and testing | Low | Medium | Medium | Monitor usage; test locally with Firebase Emulator Suite. |
| Integration testing between the front-end and the Firebase back-end | Medium | High | High | After every iteration, conduct integration testing of the front-end components with the back-end Firebase. |
| Data privacy non-compliance (PDPA Malaysia) | Low | High | High | Adhere to PDPA guidelines and ensure 2FA, data minimisation, consent mechanisms are in place. |
| Miscommunication between team members | Medium | Medium | Medium | Weekly team meetings, shared Notion/Github board, clear task Ownership. |

# 7.0 Work Breakdown Structure – Shraddha Sedhai

The following WBS rows highlight tasks assigned to Shraddha Sedhai in addition to all shared team tasks.

| WBS ID | Task / Activity | Effort (hrs) | Duration (days) | Precedence | Resources |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Determine Project Title | 1 | 0.5 | NIL | All Team |
| 1.2 | Write the Overview | 2 | 1 | 1.1 | All Team |
| 1.3 | Write Project Aims | 2 | 1 | 1.2 | All Team |
| 1.4 | Write Project Objectives | 2 | 1 | 1.3 | All Team |
| 1.5 | Write Project Scope | 2 | 1 | 1.4 | All Team |
| 1.6.1 | Derive Work Breakdown Structure | 3 | 1 | 1.5 | Group |
| 1.6.2 | Determine Milestones / Deliverables | 2 | 1 | 1.6.1 | Group |
| 1.6.3 | Derive Gantt Chart | 4 | 2 | 1.6.2 | Group |
| 1.7 | Gantt Chart File (.gan) — MILESTONE | 1 | 1 | 1.6.3 | Group |
| 1.8.1 | Development Platform & Tools | 2 | 1 | 1.6.3 | Group |
| 1.8.2 | Demonstration Platform | 1 | 1 | 1.8.1 | Group |
| 1.9 | Risk Management Plan | 3 | 1 | 1.8 | Group |
| 1.10 | Review Format & Proofread (Task 1) | 2 | 1 | 1.9 | All Team |
| 1.11 | Turnitin Check & HLMS Submission Task 1 — MILESTONE | 1 | 1 | 1.10 | All Team |
| 2.1 | Determine Functional Requirements | 2 | 1 | 1.11 | Group |
| 2.2 | Determine Non-Functional Requirements | 2 | 1 | 2.1 | Group |
| 2.3.5 | UC5 - View Notifications | 6 | 3 | 2.2 | Shraddha Sedhai |
| 2.3.6 | UC6 - Plan Weekly Meals | 6 | 3 | 2.3.5 | Shraddha Sedhai |
| 2.4 | Requirements Specification Document — MILESTONE | 2 | 1 | 2.3.6 | Group |
| 3.1 | Architectural Design (Deployment Diagram) | 4 | 2 | 2.4 | Group |
| 3.2 | Site Map (Hierarchy Diagram) | 2 | 1 | 3.1 | Group |
| 3.3.3 | Wireframes – UC3 (Browse) & UC6 (Meal Plans) | 4 | 2 | 3.3.2 | Shraddha Sedhai |
| 3.4.1 | ERD (Conceptual View) | 4 | 2 | 3.2 | Group |
| 3.4.2 | Data Dictionary | 4 | 2 | 3.4.1 | Group |
| 3.5 | Review Format & Proofread (Design) | 2 | 1 | 3.4.2 | All Team |
| 3.6 | Design Document Complete — MILESTONE | 1 | 1 | 3.5 | Group |
| 4.1 | Project Setup (React/Firebase/Git) | 4 | 2 | 3.6 | Group |
| 4.5 | Unit Testing - Iteration 1 | 4 | 2 | 4.2,4.3,4.4 | All Team |
| 4.6 | Integration Testing - Iteration 1 | 4 | 2 | 4.5 | Group |
| 4.7 | Iteration 1 Prototype Complete — MILESTONE | 1 | 1 | 4.6 | Group |
| 5.2 | Implement UC5 - View Notifications | 8 | 4 | 4.7 | Shraddha Sedhai |
| 5.3 | Implement UC6 - Plan Weekly Meals | 10 | 5 | 4.7 | Shraddha Sedhai |
| 5.4 | Unit Testing - Iteration 2 | 4 | 2 | 5.1,5.2,5.3 | All Team |
| 5.5 | System Integration Testing | 4 | 2 | 5.4 | Group |
| 5.6 | Iteration 2 Complete -MILESTONE | 1 | 1 | 5.5 | Group |
| 6.1 | End-to-End System Testing | 6 | 3 | 5.6 | Group |
| 6.2 | User Acceptance Testing (UAT) | 4 | 2 | 6.1 | All Team |
| 6.3 | Bug Fixing & Optimization | 6 | 3 | 6.2 | All Team |
| 6.4 | Documentation Finalization | 4 | 2 | 6.3 | All Team |
| 6.5 | Final Review & Proofread | 2 | 1 | 6.4 | All Team |
| 6.6 | Turnitin Check & HLMS Submission Task 2 -MILESTONE | 1 | 1 | 6.5 | All Team |

# 8.0 Project Schedule

The project spans 14 weeks and is divided into four major phases: Proposal (Weeks 1–3), Requirements & Design (Weeks 3–7), Implementation (Weeks 7–11), and Testing & Submission (Weeks 11–14). The full Gantt Chart is provided as a separate GanttProject file.

| Phase | Week Range |
| --- | --- |
| Phase 1 – Project Proposal | Weeks 1 – 3 |
| Phase 2 – Requirements Specification | Weeks 3 – 5 |
| Phase 3 – Design & Architecture | Weeks 5 – 7 |
| Phase 4 – Implementation Iteration 1 | Weeks 7 – 9 |
| Phase 5 – Implementation Iteration 2 | Weeks 9 – 11 |
| Phase 6 – Testing & Final Submission | Weeks 11 – 14 |

# 9.0 Use Cases

## Use Case 5: View Notifications

| Use Case ID | UC5 |
| --- | --- |
| Use Case Name | View Notifications |
| Goal in Context | Describes how the system delivers timely alerts to keep the user informed about expiring items, donation updates, meal reminders, and account-related activity. |
| Primary Actor | Household User |
| Pre-Condition | User is logged into the system with an active inventory, donation listings or notifications enabled. |
| Trigger | System generates a notification based on an event, or user accesses the Notifications section. |
| Typical Course of Events | 1. User opens the 'Notifications' section or clicks the notification icon. 2. System displays a sorted list of recent alerts with details and timestamps. • Inventory Alerts: items nearing expiry, move-to-donation reminders. • Donation Updates: confirmation of posted donations, notifications when a listing is claimed, pickup arrangements. • Meal Planning Reminders: alerts for planned meals. 3. User clicks a notification. 4. System opens the related screen (e.g., inventory item detail, donation request status). 5. User marks notifications as read. 6. System updates notification status and removes unread indicator. |
| Alternative Course of Events | Line 1a: If user has no new notifications, system shows: 'No new notifications. |

## Use Case 6: Food Analytics

| Use Case ID | UC6 |
| --- | --- |
| Use Case Name | Plan Weekly Meals |
| Goal in Context | Describes how users plan weekly meals using their current food inventory, reducing waste and optimising ingredient usage before expiry. |
| Primary Actor | Household User |
| Pre-Condition | User is logged into the system and has an updated food inventory. |
| Trigger | User selects 'Plan Meals' from the dashboard or receives a suggestion/alert about expiring ingredients. |
| Typical Course of Events | 1. User selects 'Plan Weekly Meals'. 2. System displays a calendar view for the week and the user's current inventory list. 3. User chooses days and meal slots (breakfast, lunch, dinner, snacks) to plan. 4. System allows user to add meals manually or browse suggested recipes based on available ingredients. 5. User selects a suggested recipe or creates a custom meal plan. 6. System updates the meal plan and links required ingredients to inventory items. 7. User confirms the plan for the week. 8. System saves the plan, updates 'reserved' quantities in inventory, and schedules reminders for each meal. |
| Alternative Course of Events | Line 5a: If no recipes match available ingredients, system displays generic recipes as suggestions. |