## 1.0 Project Overview

## FreshGuard is a smart mobile and web application to significantly reduce food waste amongst households in Malaysia. It combines intelligent stock management, expiration alerts, donation options, and responsible meal planning – and does so with strong User Data Privacy and Account Security.

## Studies carried out recently have revealed the existence of a substantial food waste in the Malaysian household sector. This is addressed directly by FreshGuard providing a single solution to log what is taken, food planning, donating surplus food to the needy and providing timely reminders when foods are on the verge of spoiling.


2.0 Project Aims

FreshGuard aims to:

- Reduce household food waste by controlling stock and alerting to the expiration of food.

- Enable individuals to make decisions when they are planning a meal about what to eat.

- Organize food surplus distribution in the community.

- Provide informative information to help users sustain their green activities.

- Ensure user’s privacy and data security by providing user-controlled account settings and 2FA authentication.

# 3.0 Project Objectives

At the project's completion, FreshGuard will:

- Implement user registration and authentication system (allowing 2FA, privacy settings) (UC1).

- Implement a detailed system of food inventory, expiry tracking and donation conversion (UC2) system.

- Implement a community food browsing module to view and take food donations which are available to them (UC3).

- Create an analytics dashboard to visualize food saving impact by charts and progress indicators (UC4).

- Design a smart notification system that will notify users of the expiration of items and remind them of the donation and remind them of the meal (UC5).Compile a weekly plan of meals using items from the inventory, breaking them down into recipes, and reminders (UC6).4.0 Project Scope

### In Scope:

- User registration, login and user privacy/security settings (including 2FA support).

- Complex food Inventory Management – add, edit and remove food inventory, mark it as used or as donation.

- Community Donation browsing: Filter, view details, request and claim donation items.
Food analytics Dashboard, visual reports on food saved and food donated.

### Out of Scope:

- Electronic commerce or payment integration for food.

- Third-party grocery store API integration.

- Delivery arrangements or food transport services.

- The ability to connect to government food waste databases.

## 5.0 Development Platform & Tools

| Component | Selected Technology / Tool |
| --- | --- |
| Utilize the framework of different frontends | React.js (Web) / React Native (Mobile) |
| Backend & Database | Firebase (Firestore, Authentication, Cloud Functions) |
| Version Control | Git with GitHub (feature-branch workflow) |
| Project Management | GitHub Projects (Kanban board), GanttProject (.gan) |
| UI Design & Wireframes | Figma |
| IDE | Visual Studio Code |
| Testing | Jest(Unit) & Cypress(E2E) & Firebase Emulator Suite |
| Demonstration Platform | Vercel (web deployment) / Expo Go (mobile preview) |

## 6.0 Risk Management Plan

| Risk | Likelihood | Impact | Priority | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| Team members are unable to work due to illness or academic conflicts | Medium | High | High | Ensure documentation is kept up to date; redistribute tasks early; make weekly check-ins. |
| Scope creep – adding features that are not in the scope | High | Medium | High | Follow scope baseline; get team leader permission for scope changes. |
| Firebase quota limits when developing and testing | Low | Medium | Medium | Keep an eye on usage, and test locally using Firebase Emulator Suite. |
| Integration testing between frontend components and Firebase backend | Medium | High | High | Use mock data for dev and conduct integration testing after each iteration |
| Follow PDPA guidelines; implement 2FA, data minimisation, and consent mechanisms. | Low | High | High | Data privacy non-compliance (PDPA Malaysia) |
| Miscommunication between team members: | Medium | Medium | Medium | Weekly team meetings; Shared Notion/GitHub board; Clear task ownership. |

## 7.0 Work Breakdown Structure

| WBS ID | Task / Activity | Effort (hrs) | Duration (days) | Precedence | Resources |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Determine Project Title | 1 | 0.5 | NIL | All Team |
| 1.2 | Write the Overview | 2 | 1 | 1.1 | All Team |
| 1.3 | Write Project Aims | 2 | 1 | 1.2 | All Team |
| 1.4 | Write Project Objectives | 2 | 1 | 1.3 | All Team |
| 1.5 | Write Project Scope | 2 | 1 | 1.4 | All Team |
| 1.6.1 | Derive Work Breakdown Structure | 3 | 1 | 1.5 | Group |
| 1.6.2 | Determine Milestoes / Deliverables | 2 | 1 | 1.6.1 | Group |
| 1.6.3 | Derive Gantt Chart | 4 | 2 | 1.6.2 | Group |
| 1.7 | Gantt Chart File (.gan) — MILESTONE | 1 | 1 | 1.6.3 | Group |
| 1.8.1 | Development Platform & Tools | 2 | 1 | 1.6.3 | Group |
| 1.8.2 | Demonstration Platform | 1 | 1 | 1.8.1 | Group |
| 1.9 | Risk Management Plan | 3 | 1 | 1.8 | Group |
| 1.10 | Review Format & Proofread (Task 1) | 2 | 1 | 1.9 | All Team |
| 1.11 | Turnitin Check & HLMS Sibmission Task 1 - Milestone | 1 | 1 | 1.10 | All Team |
| 2.1 | Determine Functional Requirements | 2 | 1 | 1.11 | Group |
| 2.2 | Determine Non-Functional Requirements | 2 | 1 | 2.1 | Group |
| 2.3.1 | UC1 - Register User & Privacy Settings | 6 | 3 | 2.2 | Simran Gopali |
| 2.3.2 | UC2 - Manage Food Inventory | 6 | 3 | 2.2 | Simran Gopali |
| 2.4 | Requirements Specification Document - MILESTONE | 2 | 1 | 2.3.6 | Group |
| 3.1 | Architectural Design (Deployment Diagram) | 4 | 2 | 2.4 | Group |
| 3.2 | Site Map (Hierarchy Diagram) | 2 | 1 | 3.1 | Group |
| 3.3.1 | Wireframes – UC1 (Register) & UC4 (Analytics) | 4 | 2 | 2.4 | Simran Gopali |
| 3.4.1 | ERD (Conceptual View) | 4 | 2 | 3.2 | Group |
| 3.4.2 | Data Dictionary | 4 | 2 | 3.4.1 | Group |
| 3.5 | Review Format & Proofread (Design) | 2 | 1 | 3.4.2 | All Team |
| 3.6 | Design Document Complete - MILESTONE | 1 | 1 | 3.5 | Group |
| 4.1 | Project Set-up (React/Firebase/Git) | 4 | 2 | 3.6 | Group |
| 4.2 | Implement UC1 - Register User & Privacy Settings | 8 | 4 | 4.1 | Simran Gopali |
| 4.3 | Implement UC2 - Manage Food Inventory | 10 | 5 | 4.1 | Simran Gopali |
| 4.5 | Unit Testing - Iteration 1 | 4 | 2 | 4.2,4.3,4.4 | All Team |
| 4.6 | Integration Testing – Iteration 1 | 4 | 2 | 4.5 | Group |
| 4.7 | Iteration 1 Prototype Complete - MILESTONE | 1 | 1 | 4.6 | Group |
| 5.4 | Unit Testing - Iteration 2 | 4 | 2 | 5.1,5.2,5.3 | All Team |
| 5.5 | System Integration Testing | 4 | 2 | 5.4 | Group |
| 5.6 | Iteration 2 Complete — MILESTONE | 1 | 1 | 5.5 | Group |
| 6.1 | End-to-End System Testing | 6 | 3 | 5.6 | Group |
| 6.2 | Testing of the Interconnection of Systems | 6 | 3 | 5.5 | Group |
| 6.3 | Market Testing (MT) | 4 | 2 | 3.1 | All Team |
| 6.4 | Documentation Finalization | 4 | 2 | 6.3 | All Team |
| 6.5 | Final Review & Proofread | 2 | 1 | 6.4 | All Team |

## 8.0 Project Schedule

The project follows a 14 week duration that is broken into 4 main sections: Proposal (Weeks 1-3), Requirements & Design (Weeks 3-7), Implementation (Weeks 7-11), and Testing & Submission (Weeks 11-14). A complete Gantt Chart is included as a separate GanttProject file (FreshGuard_Gantt.gan).

| Phase | Week Range |
| --- | --- |
| Phase 1 – Project Proposal | Week 1 - 3 |
| Phase 2 – Requirements Specification | Weeks 3 – 5 |
| Phase 3 – Design & Architecture | Weeks 5 – 7 |
| Phase 4 – Implementation Iteration 1 | Weeks 7 – 9 |
| Phase 5 – Implementation Iteration 2 | Week 9 – 11 |
| Phase 6 – Testing & Final Submission | Week 11-14 |

## 9.0 Use Cases – Simran Gopali

### Use Case 1: Register User and Privacy Settings.

| Use Case ID | UC1 |
| --- | --- |
| Use Case NameDescription | Register User and Privacy Settings: |
| Goal in Context | Describes how new users register for FreshGuard and control their privacy/security settings. |
| Primary Actor | Household User |
| Pre-Condition | The user has not been registered in the FreshGuard system. |
| Trigger | A new household user is starting the registration process. |
| Typical Course of Events | 1. User clicks on the signing link on the header. 2. System displays the registration form. 3. User inputs: Full Name, Email Address, Password, Household Size (optional). 4. System validates all the data inputs and stores the data to the database. 6. User sets privacy and security settings, and turns on 2FA. The system automatically sends an email message to the system user containing a welcome message and verification code with 6 numbers. 7. User clicks the confirmation link, types in the code and resets the password. 8. User account is activated. |
| Alternative Course of Events | Line 3a: If the email/username is already registered, system prompts the user to use a different email. Line 7a: If verification code is invalid or expired, system prompts the user to request a new code. |

### Use Case 2: Manage Food Inventory

| Use Case ID | UC2 |
| --- | --- |
| Use Case Name | Manage Food Inventory |
| Goal in Context | Captures the actions of household users when recording food items and how they keep track of their own supplies, such as converting food items which are nearing their expiration date to donations. |
| PrimaryActor | HouseholdUser |
| Pre-Condition | User is required to be authenticated, or log into the FreshGuard platform. |
| Trigger | User clicks on the Food Inventory section. |
| Typical course of events | - User selects the 'Food Inventory' option. - The user clicks on 'Food Inventory'. - User logs into the system. - System shows the food inventory dashboard.The user clicks 'Add Food Item' and enters: Item Name, Quantity, Expiry Date, Category of the food item (e.g., canned, frozen), Storage Location (optional), and Remarks/Notes. - System validates the input and stores the item in the inventory. - User accesses or modifies the list of inventory. - Inventory is displayed and can be edited and deleted. - User clicks on 'Convert to Donation' when an item is about to expire. - Asks for confirmation and makes item part of the donation list. - Displays system prompts for further information (picking-up place, availability) and completes the listing of donation. |
| Alternative Course of Events | Line 3a: If user fills out form only partially, system prints out: 'Please fill out all required fields. |